## Project setup and scope
Project Title: | FureverCare
Description: | FureverCare is an innovative pet care platform that connects busy pet owners with trusted pet service providers. The app offers seamless booking for pet sitting, grooming, and walking, along with an integrated marketplace for pet products. With user-friendly features like real-time notifications, secure payments, and expert pet care advice, FureverCare ensures a stress-free experience for both pets and their owners.
Scope
Features & Services
Booking pet services | Pet sitting, grooming, walking
Ordering pet products | Food, accessories, wellness items
Chat & notifications | Messaging system, reminders, profile features
Secure payment processing | Integrated payment gateways
Limitations
Constraint | Details
Product Inventory | Stock levels depend on supplier availability.
User Adoption | Some pet owners may prefer offline services over app-based solutions.
Internet Dependency | The app requires an active internet connection to function.
False Positives/Negatives | Environmental factors (e.g., poor lighting, wet fingers) can affect accuracy.

## Road Map
Quarter | Milestones | Sprint | Date Start | Date End | Key Teams/Person
Q1: Project Setup | Define project vision, scope, and key objectives | Sprint 1 | 2025-03-01 | 2025-03-10 | Founder, Project Manager
| Assemble development team and assign roles |  |  |  | Founder
| Establish workflow, tools, and project governance |  |  |  | Project Manager, Developer
Q2: Requirements Gathering | Conduct stakeholder meetings with pet owners, veterinarians, and pet service providers | Sprint 2 | 2025-03-15 | 2025-03-28 | Founder, Business Analyst
| Define and document functional, technical, and security requirements |  |  |  | Business Analyst, Developer
Q3: Design and Prototyping | Develop UI/UX wireframes, prototypes, and user flows for pet profiles, tracking, and reminders | Sprint 3 | 2025-04-01 | 2025-04-12 | UX/UI Designer, Developer
| Architect system infrastructure for pet activity tracking, health records, and appointment scheduling |  |  |  | Developer
Q4: Software Development Phase 1 | Implement front-end UI for pet health tracking, reminders, and vet appointments | Sprint 4 | 2025-04-15 | 2025-04-30 | Developer
| Develop and integrate back-end services and APIs for pet activity logs, medical records, and notifications |  |  |  | Developer
| Implement AI-based recommendations for pet care based on user input and data (if feasible) |  |  |  | AI Developer
Q5: Testing and Quality Assurance | Conduct unit, integration, and end-to-end testing for all pet care features | Sprint 5 | 2025-05-05 | 2025-05-20 | Developer, Tester (or outsourced QA)
| Debug, optimize, and finalize performance tuning |  |  |  | Developer
| Prepare deployment strategy, app store submission, and final review |  |  |  | Developer, Founder

## AGILE TEAMS AND ROLES
Role | Responsibilities | Team Members
Product Owner | Defines product vision, prioritizes backlog, and ensures customer needs are met. | Ylanan, Ymir Onil
Scrum Master | Facilitates Agile processes, removes blockers, and ensures smooth workflow. | Patalinghog, Ryan
Developers | Build, test, and deliver features for the pet care app and services. | Nabua, Clark and Tejam, Gab
UI/UX Designer | Designs user-friendly interfaces and user experiences for the app. | Lasmarias, Brent
QA Tester | Ensures quality by testing features, identifying bugs, and verifying fixes. | Bonachita, Viscount
Marketing Specialist | Develops marketing strategies, manages social media, and customer outreach. | Agbay, Greorge

## MEETINGS
Date | Meeting Type | Start Time | End Time | Duration | Participants
2001-03-01 | Sprint 1 Planning | 9:00 | 10:30 | 1.5 hrs | Founder, Project Manager, Developer
March 3-7 | Daily Scrum (Sprint 1) | 9:30 | 9:45 | 15 mins | Project Team
2010-03-01 | Sprint 1 Review & Retro | 15:00 | 16:00 | 1 hr | Project Team
2015-03-01 | Sprint 2 Planning | 9:00 | 10:30 | 1.5 hrs | Founder, Business Analyst, Developer
March 17-21 | Daily Scrum (Sprint 2) | 9:30 | 9:45 | 15 mins | Project Team
2022-03-01 | Stakeholder Meeting | 14:00 | 15:00 | 1 hr | Founder, Business Analyst, Pet Owners
2028-03-01 | Sprint 2 Review & Retro | 15:00 | 16:00 | 1 hr | Project Team
2001-04-01 | Sprint 3 Planning | 9:00 | 10:30 | 1.5 hrs | UX/UI Designer, Developer
April 2-5 | Daily Scrum (Sprint 3) | 9:30 | 9:45 | 15 mins | Project Team
2010-04-01 | Mid-Sprint Check-in | 14:00 | 14:30 | 30 mins | Project Team
2012-04-01 | Sprint 3 Review & Retro | 15:00 | 16:00 | 1 hr | Project Team
2015-04-01 | Sprint 4 Planning | 9:00 | 10:30 | 1.5 hrs | Developer
April 16-19 | Daily Scrum (Sprint 4) | 9:30 | 9:45 | 15 mins | Project Team
2022-04-01 | Stakeholder Meeting | 14:00 | 15:00 | 1 hr | Founder, Developer, Pet Owners
1930-04-01 | Sprint 4 Review & Retro | 15:00 | 16:00 | 1 hr | Project Team
2005-05-01 | Sprint 5 Planning | 9:00 | 10:30 | 1.5 hrs | Developer, Tester (QA)
May 6-9 | Daily Scrum (Sprint 5) | 9:30 | 9:45 | 15 mins | Project Team
2012-05-01 | Performance Tuning Check-in | 14:00 | 14:30 | 30 mins | Developer
2015-05-01 | Deployment Prep Meeting | 15:00 | 16:00 | 1 hr | Founder, Developer
2020-05-01 | Final Review & Launch Prep | 14:00 | 15:00 | 1 hr | Founder, Developer, Compliance Team
[6 empty] | Sprint | Duration | Key Deliverables | Teams Involved
[6 empty] | Sprint 1 | 01-Mar-25 – 10-Mar-25 | Define project vision, scope, and objectives | Founder, Project Manager
[8 empty] | Assemble development team and assign roles | Founder
[8 empty] | Establish workflows, tools, and governance | Project Manager, Developer
[6 empty] | Sprint 2 | 15-Mar-25 – 28-Mar-25 | Conduct stakeholder meetings (pet owners, veterinarians, pet service providers) | Founder, Business Analyst
[8 empty] | Define functional, technical, and security requirements | Business Analyst, Developer
[6 empty] | Sprint 3 | 01-Apr-25 – 12-Apr-25 | Design UI/UX for pet profiles, tracking, and reminders | UX/UI Designer, Developer
[8 empty] | Architect system infrastructure for pet tracking, health records, and scheduling | Developer
[6 empty] | Sprint 4 | 15-Apr-25 – 30-Apr-25 | Develop front-end UI for pet health tracking and vet appointments | Developer
[8 empty] | Integrate back-end services for pet activity logs, medical records, and notifications | Developer
[8 empty] | Implement AI-based pet care recommendations (if feasible) | AI Developer
[6 empty] | Sprint 5 | 05-May-25 – 20-May-25 | Conduct unit, integration, and end-to-end testing | Developer, Tester (or outsourced QA)
[8 empty] | Debug, optimize, and finalize performance tuning | Developer
[8 empty] | Prepare deployment strategy, app store submission, and final review | Developer, Founder

## Focus group discussion
Section | Details
Objective | Gather insights from pet owners about their needs and expectations for pet care services.
Date & Time | March 15, 2025 - 2:00 PM to 4:00 PM
Location | Zoom Meeting (Link to be provided)
Facilitator | [Your Name or Assigned Team Member]
Participants | - Pet owners
- Veterinarians
- Pet service providers
Discussion Topics | - Challenges pet owners face
- Features they want in a pet care service
- Preferred booking & payment methods
- Trust factors for pet care providers
Expected Outcomes | - Identify key user pain points
- Validate business assumptions
- Improve service offerings

## TestCase
Test Case ID | Module | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status (Pass/Fail) | Comments
Test 01 | Authentication | Verify successful login with valid credentials | 1. Open app 2. Enter valid email 3. Enter valid password 4. Click Login | Email: user@example.com Password: ValidPassword123 | User should be redirected to home dashboard
Test 02 | Registration | Verify if the Registration is valid | 1. Start registration 2. Use existing email 3. Complete other fields | Email: user@example.com | Registration successful
Test 03 | Booking | Verify pet service booking functionality | 1. Select 'Book Service' 2. Choose service type 3. Select date/time 4. Confirm booking | Service: Dog Walking Date: [future date] Time: 10:00 AM | Booking confirmation with details should appear
Test-04 | Profile | Verify user profile creation | 1. Open app 2. Click 'Create Profile' 3. Fill all required fields 4. Save profile | Name: John Doe Email: john@example.com Phone: +1234567890 | Profile should be saved and visible in 'My Profile' section
Test 05 | Notifications | Verify booking reminder notification | 1. Create booking 2. Wait for reminder time | Booking set for tomorrow 10:00 AM | Notification should appears
Test 06 | Marketplace | Verify product purchase flow | 1. Browse products 2. Add item to cart 3. Proceed to checkout 4. Complete payment | Product: Dog Food (5kg) | Order confirmation should appear with estimated delivery date

## Software Design (hidden)
S